## Lost Opportunity Worksheet
PROJECT NAME
WBS | Task Description | Resource | Planned Duration(h) | Missed Duration(h) | Planned Value | Missed Value | Depen-dencies Y/N | Cost Loading/h | 16 | COMMENTS
1.3.2 | Rationalise all SIC codes to match advertising campaigns | TonyF | 36 | 12 | 4500 | 1500 | Y | 125 | 12
1.5.5 | Create acceptance test plan | Sunder | 16 | 4 | 1520 | 380 | Y | 95 | 4
1.5.9 | Document transition procedures | JaneP | 8 | 1 | 600 | 75 | N | 75
|  |  | 60 | 17 | 6620 | 1955
| Total Lost Opportunity due to unplanned variance |  | 29.53%
| ADDED COSTS (Optional) |  | IMPACT | [6 empty] | COMMENTS
| Business Value (e.g. Revenue at Risk): | 2500000
| Resource Resolution Days Duration: | 6
| Maximum Task Hold In Days: | 10
| Resolution Resources: | 3
| Average Resolution Resource Per Hour Rate: | 75
| Average Percent Time To Resolve: | 20%
| Miscellaneous Costs: | 1400
| Total Missed Duration in Days: |  | 32 | <Days
| Planned Project Delivery Date: | 2005-11-04 | 2005-12-06 | <NEW Delivery Date
| Customer Promise Date: | 2005-11-11 | 25 | <Days Past Due
| Estimated Total COST IMPACT: | 2503625
Formulas:
IMPACT = IF(C22="","",C22+[IMPACT, row above])

## Worksheet Instructions
The following worksheet was created by Team Delta for the On-line version of PMI's Managing Multiple Projects course in December 2004 (Carl Pritchard, Instructor). For more information on the course and how/why this worksheet was developed, contact Carl at carl@carlpritchard.com or 301-606-6519.
The instructions for use are quite simple. From the project's work plan:
Enter the task information
Enter the resource information including rates
Enter the planned duration for the tasks impacted by the loss of the resource
Enter the missed duration (actual hours that were diverted from other efforts to fill the gap)
The calculations will show decision makers the result of resource conflicts.
The calculations can also provide a basis for contingency to build into the next project if the same risk exists
The "Added Costs (Optional)" section attempts to calculate the IMPACTS of (resource assignment) resolution costs, potential revenue loss when a customer promise date applies, and calculates the new project date based on the delay where other tasks are dependent upon the affected resource losses. Below is a key to these fields:
COLUMNS
Column H: Dependencies: Must = "Y" to be included in the duration impact calculations below. They will push out the "Project Delivery Date". The calculation assumes the "Y's" are not scheduled in parallel in the project plan.
Column L is hidden and adds up the days missed durations that equal "Y".
All Red Marked entries are calculated.
ROWS
Business Value (e.g. Revenue at Risk): Business opportunity achieved (in dollars) by delivering by the Customer Promise Date.
Resource Resolution Days Duration: Time in days it takes to make a decision about resource assignments including the time the resource(s) is/are no longer meeting their commitment on the current project.
Maximum Task Hold Days: Once the staffing decision is made, enter the number of days it takes to actually staff the task so that it is fully picked up on the project. This may include the number of days it takes to bring resources up to speed on the project and tasks as well as training where applicable.
Average Resolution Resource Per Hour Rate: Average per hour rate in dollars of the persons working to resolve the resource assignment issue.
Average Percent Time To Resolve: Average time spent by all resolving resources combined.
Miscellaneous Costs: Costs to the project directly caused by the task delays that should be captured/noted.
IMPACT Total Missed Duration in Days: Missed Duration + Maximum Task Hold (re-staff lead time) + Resource Resolution Days Duration.
Planned Project Delivery Date per project plan
IMPACT Planned Project Delivery Date is calculated based on Planned Project Delivery Date + Total Missed Duration in Days.
Customer Promise Date per project agreement and project plan
IMPACT Customer Promise Date is the calculated difference between the IMPACT Planned Project Delivery Date minus the Customer Promise Date.
Estimated Total Cost Impact: Missed Value + (Resolution Resources x Average Resolution Resource Per Hour Rate x Average Percent Time To Resolve) + Business Value (e.g. Revenue at Risk) + Miscellaneous Costs.