The templates below were generated by the Managing Multiple Projects class offered in Cincinnati, Ohio in January 2002.  The first (Status Report) was provided through the generosity of Rick Talbot, PMP, whose team modeled their classwork after his efforts.

My apologies that one of the team efforts was illegible in the screen capture I did during your work.  The rest are incorporated below.  I also encourage you to peruse the work of your peers in other MMP classes available on the Postings Board.

Carl Pritchard

carl@carlpritchard.com

www.carlpritchard.com

| Project Name: | Project #: |
| --- | --- |
| Sponsor: | Manager: |
| Date Revised: | Revised by: |

| Start Date |  | Original Target Date |  | Revised Target Date |  | 2001 Release Dates |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Vital Project Component | Grade | Comments |
| --- | --- | --- |
| Schedule | A |  |
| Cost | A |  |
| Scope Quality | A |  |
| Team Commitment | A |  |

Grading Scale: A = Progressing as Planned			D = Not Progressing as plan / Immediate review for resolution

B = Progressing as Planned with modifications	F = No Progress / High Level project evaluation required

C = Planned Progression in Jeopardy

# Executive Summary

During last week the major highlights are:

- Project is slightly behind schedule due to additional reviews of the web page mockups.  These additional reviews should reduce the design time, and thus no corrective action is necessary.

- Conducted Placeware conference call with the external agents to prototype the web pages.

- An issue has arisen with the ability to interface with the ABC Company who only uses XYZ record layouts.

# Milestones/Deliverables

Below is the status of the deliverables that were either recently completed or are actively being developed.

| Deliverable | Planned Start Date | Planned Completion Date | Actual Start Date | Target/Actual Completion Date | Comments/ Status |
| --- | --- | --- | --- | --- | --- |
| Storyboard | 9/10/01 | 9/30/01 | 9/14/01 | 9/28/01 | On schedule |
| Web Pages | 9/10/01 | 12/03/01 | 9/17/01 | 12/10/01 | 1 Week Behind |
| Reports | 10/01/01 | 01/01/02 | 10/3/01 | 12/21/01 | 1 Week Ahead |
| Interfaces | 12/01/01 | 02/02/01 |  |  | Not Started |

# Issues:

Issue:

Date Reported:

Reported By:

Targeted Resolution Date:

Actual Resolution Date:

Impact:

Action/Comments:

# Deliverable Acceptance

Below are the deliverables that have been recently completed or will be completed in the next several weeks.

| Deliverable | Completion Date | Approval Date | Earned Value | Comments/ Status |
| --- | --- | --- | --- | --- |
| Storyboard | 9/25/01 | 9/28/01 | $2,000 |  |
| Web Pages | 11/10/01 | Pending | $4.235 | Core Team is reviewing |
| Reports |  |  |  |  |
| Interfaces |  |  |  |  |

# Change Requests

Below are the change requests that have been recently submitted during the last several weeks.

| Change Request | Submitted Date | Approval/ Disapproval Date | Schedule Impact | Cost Impact | Comments/ Status |
| --- | --- | --- | --- | --- | --- |
| Submitted Quote Window | 11/14/01 | Pending | 500 hours | $10,000 | Rick Wagner is reviewing |
| Modify or Delete Submitted Quotes | 11/14/01 | Pending | 200 hours | $4,000 | Christy Schuldt is reviewing |

# Plans for Next Week

COMMMENTS (SUMMARY OF THE CURRENT PROJECT STATUS, TO BE INSERTED INTO THE DATABASE):

Snap-Shot of Events

| Target Date Changed? |  | Date, if new: To be determined with a new schedule. |
| --- | --- | --- |
| Grades Changed? | No | If “yes”, note above |
| Priority Changed? |  |  |
| Approval Changed? |  |  |
| Phase Changed? |  |  |
| Step With-in Phase Changed? |  |  |
| Sponsor Changed? |  |  |
| Project Manager Changed? |  |  |
| Business Analyst Changed? |  |  |
| Originating Business Area Changed? |  |  |

| Issue Escalation Form |
| --- |
| ID: Project ID: Name or Number | Date Opened: | , 20 |
| Title: Unique Issue Identifier/Title | Org. Target: | , 20 |
| Issue Description | Current Target: | , 20 |
|  | Completion Date: | , 20 |
|  | <Note: Define “target” versus “completion date” and insert definition here> |
| Initiator: | Name/E-mail of Person who Identified Issue |
| Owner: | Name/E-mail of Person who Owns Related Tasks |
| Assignee: | Name/E-mail of Person responsible for resolution |
| Recommended Resolution: | As defined by Owner and Assignee |
| Final Resolution: | To be completed ONLY when outcome clear |
| Risk Level before Resolution |  |
| Projected Risk Level after Resolution |  |
| Current Status |  |

PROCESS:

- Prioritize Issues

- Central Repository

- Tracking

- Assign Owner

- Tool for Issue Analysis

| Change Control – Project Change |
| --- |
| Requestor Name: | Name/E-mail of individual requesting change |
| Request Date: | , 20 |
| Change Description |
| Reason for Change: | Clearly define the business reasons for implementing the change, including names/e-mails of any critical players |
| Change Impact: | Specific savings/revenues to be realized as a result of the change or behavioral improvements promoted by the change |
| Need by Date: | , 20 | Approved for Analysis: | , 20 |
| Functional Impact of Change: | Functional Area affected:Name of Functional Organization Functional Area affected:Name of Functional Organization |
| Schedule Impact: | # Days: | Cost Impact: | $, |
| Approved by: | Name/E-mail of approving authority |
| Signature: |  |
| Denied by: | Name/E-mail of responsible authority |
| Signature: |  |
| Deferred by: | Name/E-mail of responsible authority |
| Deferral Review Date: , 20 |
| Signature: |  |

NOTE: Please refer to process notes below.

Notes on applying the Change Control Template

- Have a defined owner to approve request submittal

- Complete the template

- Review the database of changes

- PM to make assignments, based on prioritization process

- Perform analyses

- Approve, deny or backlog the change

- Implement the approved changes

- If not successful, back out the change

| Change Request Template |
| --- |
| CHANGE REQUEST |
| Project Name: | Project ID: Name or Number |
| Project Manager: | Name/E-mail of project manager |
| Requestor Name: | Name/E-mail of individual requesting change |
| Date: | , 20 |
| Description of Change: | Full description of the nature of the change and how it will impact the project scope |
| Reason for Change: | Specific savings/revenues to be realized as a result of the change or behavioral improvements promoted by the change |
| Date Required by: | , 20 |
| EVALUATION SECTION |
| Routing: | Name/E-mail of Evaluator |
|  | Name/E-mail of Evaluator |
|  | Name/E-mail of Evaluator |
|  | Name/E-mail of Evaluator |
| Impact Assessment |  |
| Cost: | $, |
| Schedule: | # Days: |
| Resource: | # Resource-Days Affected: Name/E-mail of resource(s) affected |
| Risks: | Specific risks created/affected |
| Team Recommendation: |  |
| Notes/Alternatives: | Specific rationale for team recommendations or dates for deferred change |
| APPROVAL SECTION |
| Result: |  |
| Sign-offs: | Sponsor: | Name/E-mail of Sponsor |
| Date: , 20 | Signature: |  |
|  | PM: | Name/E-mail of PM |
| Date: , 20 | Signature: |  |
|  | Customer | Name/E-mail of Customer |
| Date: , 20 | Signature |  |
| Distribution: |  |

| Time Reporting |
| --- |
| Name: | Team Member Name | Week Ends Sunday |
| ID: | Team Member ID or SSN | Period |
| Project ID: | Project ID Number | , 20 |
| Project Name: | Project Name |
| Phase: | Project Phase |
| Project Tasks: | Task Name or WBS ID Task Name or WBS ID Task Name or WBS ID Task Name or WBS ID | Hours (Reg): | Hours (OT): |
| Non-Project Tasks: | Task Name or Activity Task Name or Activity Task Name or Activity Task Name or Activity | Hours (Reg): | Hours (OT): |
|  |  | TOTALS: |  |
| Approval: |
| PM: | Name/E-mail of PM | Initials: |  |
| Management: | Name/E-mail of Authority | Initials: |  |
| Return: |
| Date: | , 20 |  |
| Reason: |  |

Waterfall Schedule Template

1.0  Project Name

  - Project initiation

    - Business case

    - Charter

    - Scope

  - Project Planning

    - Requirements

    - WBS

    - Risk Assessment

    - Change Control

  - Project Execution

    - Analysis

    - Design

    - Development

    - Test

    - User Acceptance Test

  - Project Close

    - Lessons Learned

    - Closing Project

    - Wrap-up Party!

| Weekly Status Report |
| --- |
| Project Name |  |
| Project Number |  |
| Overall Project Status |  |
| This Week’s Accomplishments |  |
| Key Issues: |  |
| Next Week’s Planned Accomplishments |  |
| Closed Issues |  |
| Number of Change Requests |  |
| Comments |  |