## Sheet1
Risk Checklist generated by PMI Atlanta Class- Atlanta, GA | [5 empty] | Action Items
"Yes" represents a potential trouble spot | PLACE "X" in Appropriate Column
REQUIREMENTS | Yes? | No?
Were key stakeholders not available or excluded during requirements definition? |  |  | 0 |  |  | 0
Are delivery of requirements being performed by an outside provider? |  |  | 0 |  |  | 0
Was the formal signoff of requirements eliminated? |  |  | 0 |  |  | 0
Was the stakeholder analysis skipped? |  |  | 0 |  |  | 0
Have new requirements been identified since project kickoff? |  |  | 0 |  |  | 0
Can any of the new requirements affect scope? |  |  | 0 |  |  | 0
No WBS dictionary exists? |  |  | 0 |  |  | 0
Is there a high probability that the sponsor (or other significant stakeholder) could change? |  |  | 0 |  |  | 0
REQUIREMENTS
|  |  |  | Yes | No
|  |  |  | 0 | 8
RESOURCES
Q1: Is it a key Resource? |  |  | 0 |  |  | 0
Q2: Is there the potential for a long term absence? |  |  | 0 |  |  | 0
Q3: Do we not have suitable replacements? |  |  | 0 |  |  | 0
Q4: Is the resource assigned to the critical path tasks? |  |  | 0 |  |  | 0
Q1: Does the vendor have higher priority clients? |  |  | 0 |  |  | 0
Q2: Is Vendor known to deliver late? |  |  | 0 |  |  | 0
Q3: Is vendor located in a part of the world that is volatile? |  |  | 0 |  |  | 0
Q4: Are vendors resources unstable? |  |  | 0 |  |  | 0
Q1:Is management unaware of vacation schedules for all resources? |  |  | 0 |  |  | 0
Q2: Are there no replacements available? |  |  | 0 |  |  | 0
Q3: Will this affect schedule + deliverables? |  |  | 0 |  |  | 0
Q4:Will this affect quality? |  |  | 0 |  |  | 0
Q1: Is no backup equipment available? |  |  | 0 |  |  | 0
Q2: Can vendor replace equipment ASAP? |  |  | 0 | RESOURCES |  | 0
Q3: Is there an alternate vendor? |  |  | 0 | Yes | No | 0
Q4: Are funds not available for repair/replacement? |  |  | 0 | 0 | 17 | 0
Q5: Is replacement/implementation of new equipment not lengthy? |  |  | 0 |  |  | 0
BUDGET
Q1: Is the budget based on expired estimates? |  |  | 0 |  |  | 0
Q2:Are resource contracts pending |  |  | 0 |  |  | 0
Q3:Are Resource costs volatile? |  |  | 0 |  |  | 0
Q4:Is scope Nebulous |  |  | 0 |  |  | 0
Q1:Have you Failed Previous audits |  |  | 0 |  |  | 0
Q2: Have you neglected your internal audit system? |  |  | 0 |  |  | 0
Q3: Are your records out of date/incomplete? |  |  | 0 |  |  | 0
Q4: Have you failed to designate resources to compliance? |  |  | 0 |  |  | 0
Q5: is there growing federal attention to your budget area? |  |  | 0 |  |  | 0
Q1: Is the budget based on expired estimates? |  |  | 0 | BUDGET |  | 0
Q2:Are resource contracts pending |  |  | 0 | Yes | No | 0
Q3:Are Resource costs volatile? |  |  | 0 |  |  | 0
Q4:Is scope Nebulous |  |  | 0 | 0 | 13 | 0
SCHEDULE
Q1. Is equipment overdue? |  |  | 0 |  |  | 0
Q2. Is installation behind schedule? |  |  | 0 |  |  | 0
Q3. Are there other higher priority projects? |  |  | 0 |  |  | 0
Q4. Does the customer have no fallback plan? |  |  | 0 |  |  | 0
Q1. Does vendor have higher priority clients? |  |  | 0 |  |  | 0
Q2. Is the vendor known to deliver late? |  |  | 0 |  |  | 0
Q3. Is vendor located in part of the world that is volatile |  |  | 0 |  |  | 0
Q4: Are vendors resources unstable? |  |  | 0 |  |  | 0
Q1. Do we have to order equipment from external vendor |  |  | 0 | SCHEDULE |  | 0
Q2. Is material from sole source (or non=preferred) vendor? |  |  | 0 | Yes | No | 0
Q3, Is this new technology |  |  | 0 | 0 | 13 | 0
Q4. Is material delivered historically late? |  |  | 0 |  |  | 0
Q5. Is vendor backlogged now? |  |  | 0 |  |  | 0
Overall Score
|  |  |  | 0 | 51