## Risks
AREA | WEIGHT | YOUR SCORE (3,2,1) | Weighted Score
Security | 5 | 2 | 10
3 - There are external interfaces that may lead to potential breaches
2 - In between
1 - Purely internal system and work
Staffing | 4 | 3 | 12
3 - One third or more of positions are unfilled
2 - In between
1 - there is a waiting list of qualified applicants
Technical Challenge | 3 | 2 | 6
3 - Completely new endeavor - Never been done
2 - In between
1 - Been there, done that, got the t-shirt
Deadline | 4 | 1 | 4
3 - Scope is undefined and project is not yet approved/sponsored
2 - Scope is undefined or project is not yet approved/sponsored
1 - Scope is defined and project is sponsored/approved
WEIGHTED SCORE
32

## Opportunities
CATEGORY | WEIGHT | YOUR SCORE | Weighted Score
Morale | 3 | 2 | 6
3 - Personnel outside the project want in
2 - In between
1 - Personnel inside the project want out
Public Service | 4 | 2 | 8
3 - There is a direct contribution to individual and public welfare
2 - In-between
1 - Internal - No public impact
Client Trust and Image | 5 | 2 | 10
3 - Follows only established processes and procedures (e.g., ISO, CMM)
2 - All in-between
1 - No established process or procedure
Business | 3 | 2 | 6
3 - Product/Output in high demand
2 - All in-between
1 - There's already and oversupply or glut of the product/output
Weighted Score
30